Lasswade ASG Agreed Improvement Action Plan for Session 2018-19

| Priority No. | QI | Priority | Expected outcomes for learners which are measurable or observable |
| --- | --- | --- | --- |
| 1 | 2.2 | Construction of a consistent and coherent BGE Science Curriculum This priority assumes the Social Studies work is completed by October 2018 to allow capacity issues in schools to be addressed | Experience of consistent Science curriculum. Learners will accurately know which level they have achieved in Science and what their next steps in learning are. There will be a smooth and coherent transition into S1 from P7 in the Lasswade ASG primaries. |

| Tasks to achieve priority | Timescale and checkpoints | Those involved – including partners | Resources and staff development |
| --- | --- | --- | --- |
| Form short-life working group | By December 2018 | ASG HTs to appoint 1 person per school to join group led by PT Science BGE (LHS) | Initial meeting to be called by PT Science BGE in November 2018. ASG HTs to ensure that a representative from each primary school can attend the group’s meetings. |
| Aims and objectives of working group to be presented to ASG HTs | December 2018 | PT Science BGE (LHS) | To come from working group meeting(s) |
| Mapping of key assessment points across BGE within Science | March 2019 | Working Group | Identified members of Working Group to lead mapping of assessment points using Benchmarks. 1 day time will be required per member of staff. |
| Structure of Science curriculum to be revised using the experiences and outcomes to correlate with the benchmarks and key Science related skills | March 2019 March 2019 | Working Group Checkpoint with ASG HT Meeting | 3 planning days for identified members of staff to visit schools/local authorities and draw from practice there. Group can use resources currently in place to construct a new common curricular structure for Science |
| Presentation of revised curriculum and assessment strategy to ASG HTs | April 2019 | Working Group with ASG HTs | Identified members of Working Group may require 1 planning day for preparation of this event. LHS staff to offer CLPL support for ASG primary staff. |
| Evaluation of the short-life working group | May 2019 | ASG HTs with PT Science BGE (LHS) | Evaluation to be conducted and presented to ASG HT Meeting. |
| Evidence of Impact on learners – How do we know? |
| Evaluative survey of pupils’ attitudes and opinions within Science (session 2018/19 during implementation). Feedback of opinions from primary school staff regarding the consistency and coherence of the curriculum and confidence within this including use of the benchmarks and assessment strategies to gauge progress. |

| Priority No. | QI | Priority | Expected outcomes for learners which are measurable or observable |
| --- | --- | --- | --- |
| 2 | 2.3 | Create a shared understanding and consistent approaches to the learning and teaching of numeracy across the Lasswade ASG | A wide range of creative approaches and strategies used to develop, increased engagement, motivation and attainment in numeracy. Skilled questioning is used to improve engagement of all our learners. |

| Tasks to achieve priority | Timescale and checkpoints | Those involved – including partners | Resources and staff development |
| --- | --- | --- | --- |
| Establish the role and remit for our ASG Numeracy Development Officer and Numeracy Co-ordinators | June 2018 | Sub Group of ASG HTs Y Sommerville | The ASG will fund this post – approximately £18,000 (2 day post) Supporting the creation and purchasing of materials to support the SEAL implementation across the ASG |
| Audit of current position in each ASG school regarding SEAL training, materials and implementation | August 2018 | Numeracy Development Officer Numeracy Co-ordinators/HT/PT Mathematics as appropriate | Email questionnaire followed by visits/meetings as appropriate |
| Create and deliver a training programme which supports the needs of each staff group Teachers with no SEAL experience Teachers with SEAL experience Non teaching staff | August 2018 | All primary staff/nursery staff All secondary maths Volunteer staff from other secondary curricular areas Numeracy co ordinators working with our ASG development officer for numeracy | SEAL training – no previous experience - teaching staff/ nursery staff – SDDCWs 10 hours Previously SEAL trained – 10 hours Support staff and CCDWs – 4 hours Five sessions agreed 1.15pm to 3.15pm 21/09/18 05/10/18 22/10/18 (Support Staff and CCDWs) 07/01/19 (Support Staff and CCDWs) 22/03/19 |
| Staff apply findings from educational research and CLPL training to improve learning and teaching practice | September 2018 – March 2019 | All primary staff/nursery staff All secondary maths Volunteer staff from other secondary curricular areas Numeracy co-ordinators working with our ASG development officer for numeracy | Staff access to SEAL training materials including Specifically 10 hours in working time agreement for professional reading (balance time) Creating and purchasing materials to support the SEAL implementation |
| Identify dates in the annual calendar for regular drop in sessions for staff within the ASG across all CfE levels in between training sessions to allow staff additional opportunities to engage in professional dialogue and develop understanding | October 2018 – April 2019 | Numeracy co-ordinators working with our ASG development officer for numeracy | CLPL |
| Numeracy development in early years. Alongside SEAL training, develop a consistent language of learning within numeracy which is used across all ASG nurseries. | September 2018 – March 2019 | HT – Mount Esk and SCCDWs within ASG | CLPL for SCCDWs |
| The Lasswade ASG will develop a clear vision statement to shape high quality learning and teaching within numeracy. | August 2018 – June 2019 | ASG HTs and ASG Numeracy Development Officer | ASG Meetings Survey Monkey Questionnaire |

Evidence of Impact on learners – How do we know?

A sample cohort of pupils from P1,4, 7, S1 & S3 from each ASG school Survey Monkey Questionnaire at the start and end for staff Staff are required to demonstrate they have developed a wide range of strategies and approaches and can deliver this, in order to improve the quality learning and teaching experiences of their learners in order to improve the teaching of numeracy, evidenced through the SQUIP of each ASG school